## Slide 1: Randolph Sanitary Sewer Project
Special Council Meeting February 24th

## Slide 2: SCHEDULE
Open House – March 30th & 31st, 2022
Accept Feasibility Report / Order Plans & Specs – May 25, 2022*
Develop Plans and Specifications – May – January 2022
Finalize Plans and Specifications – February 2023
Approve Plans and Authorize to Bid – February 24th, 2023*
Open Bids – March 2023
Award Bid– April 2023*
Open House (What to Expect During Construction) – April/May 2023
2023 Construction - May 2023 – October 2023
2024 Construction - May 2024 – October 2024

## Slide 3: HOW DID WE GET HERE?
Existing failing septic systems
  Old Zoning Practices didn’t account for a secondary septic site
October 2020 Bonding Bill
City Council Accepted Bond at November 19th Special Council Meeting
County Project on CSAH 88
Field Survey & Questionnaires
March Open House
Feasibility Report May 25th

## Slide 4: EXISTING CONDITIONS
Typically 20’ Wide Roadway
No formal storm sewer
  Ditches & culverts, relies on infiltration into ground
Watermain installed in 1978
  Unlocatable, plans based off Asbuilts
  Typically 6”

## Slide 5: WATERMAIN
  Replacement Cost is Approximately $3.6 million
    Impact to Taxes would be approx. $1,385/Yr per property
  Watermain replacement is NOT proposed with project
  Contractor will be required to pothole watermain prior to beginning work
  Some spot replacement to relocated hydrants on CSAH 88

## Slide 6: WATER SERVICES
  Water services impacted by installation of Sanitary sewer will be replaced to ROW
  During construction, all homes will be placed on temporary water system
  Only short-term water outages are expected

## Slide 7: SANITARY SEWER IMPROVEMENTS
Sanitary Sewer in Street 10’-20’ deep
Sewer Services Stubbed to Approx. ROW
Flows to city hall parking lot, Pumped to Stabilization Ponds

## Slide 8: Sanitary Sewer Services
Only properties with a failing septic system will be required to connect
Connections Beginning in 2024
  Notification in the mail when system is tested & ready
County Assistance Program
Full Service Owned by Property
ROW LINE
Service Stub with Project
Homeowner Connection

## Slide 9: STORM SEWER – CITY
  Installation of City-wide storm sewer cost is Approx $3.6 million
    Impact to Taxes would be $1,385/Yr per property
  Storm sewer on local streets is NOT proposed
  Curb and gutter NOT proposed
  Some drainage nuisances will still exist

## Slide 10: STORM SEWER – CSAH 88

## Slide 11: LOCAL STREET IMPROVEMENTS
City streets will match the existing width(20’ min)
No curb & gutter is proposed
Reinstate the existing swales and ditches
Sidewalks impacted by project will be replaced
Existing signs will be reinstalled

## Slide 12: LOCAL STREET IMPROVEMENTS

## Slide 13: CSAH 88 STREET IMPROVEMENTS
4’
4’
10’
10’
PARKING LANE
PARKING LANE
DRIVE LANE
DRIVE LANE

## Slide 14: CSAH 88 STREET IMPROVEMENTS

## Slide 15: CSAH 88 PEDESTRIAN IMPROVEMENTS

## Slide 16: Estimated Project Cost
 |  | CITY OF RANDOLPH | DAKOTA COUNTY
ESTIMATED CONSTRUCTION COST |  | $9,539,876 | $6,036,848
10% CONTINGENCY |  | $953,990 | $603,690
 |  | $17,134,404 | 
PRELIMINARY DESIGN, FINAL DESIGN, GEOTECHNICAL |  | $746,794 | $298,145
LAND ACQUISITION (ESTIMATED) |  | $1,000,000 | 
CONSTRUCTION ADMINISTRATION (ESTIMATED) |  | $650,000 | $151,480
TOTAL ESTIMATED PROJECT COST: |  | $12,890,660 | $6,640,538

## Slide 17: Requested Action
Approve the plans and project specifications and authorize advertisement for bids

## Slide 18: Thank You! Questions?
Matt Blazer, P.E.
Consultant City Engineer
612-756-4823
Matt.blazer@bolton-menk.com